## Main Project Plan
Activity	plan		Actual

	Start Date	End Date	Start Date	End Date
1. ARM presentations	14-11-2017	16-11-2017	14-11-2017	22-11-2017
1.1 Memory Hierarchy
1.2 Memory Management Unit
1.2.1 Translation Lookaside Buffer
1.3 Page
1.3.1 Page fault
1.3.2 Demand paging
1.4 Cache
1.4.1 Non-cached system
1.4.2 Cached system
1.4.3 Write buffer
2. Linux Driver basic Presentation	16-11-2017	20-11-2017	16-11-2017	22-11-2017
2.1 Data Types in the Kernel
2.2 USB Drivers
2.2.1 Structure of USB Device Driver
2.2.2 URB (USB Request Block)
2.3 The Linux Device Model
2.3.1 Bus
2.3.2 Device
2.3.3 Device Drivers
2.3.4 Class
2.4 DMA
2.5 Block Drivers
2.5.1 Registration
2.5.2 Block device operations
2.5.3 Request processing
2.5.4 Other details
3. Environment setup and various boot options like tftp,nfs,mmc,uart,cross compilation.	20-11-2017	27-11-2017	22-11-2017	27-11-2017
4. Linux pseudo code Character driver and app , unit and functional testing .	27-11-2017	05-11-2017	28-11-2017	08-12-2017
5. USB
5.1 USB Basics (usb types ,speed and types of endpoints)	12-12-2017	12-12-2017	12-12-2017	12-12-2017
5.2 USB Enumeration flow	13-12-2017	13-12-2017	13-12-2017	13-12-2017
5.3 USB Descriptors	14-12-2017	14-12-2017	14-12-2017	15-12-2017
5.4 USB Device classes	18-12-2017	18-12-2017	18-12-2017	18-12-2017
5.5 How Host will identify the particular USB device	19-12-2017	19-12-2017	19-12-2017	26-12-2017
5.5 USB video class (UVC) Driver code flow analysis	26-12-2017	29-12-2017	26-12-2017	04-01-2018
6. USB Driver Implementation
6.1 Actual USB Video class driver implementation	05-01-2018	12-01-2018
6.2 UVC driver Debugging (GDB)	16-01-2018	16-01-2018
6.3 UVC driver Testing(Kernel mem leak and profiling tools, static analyzer tools)	17-01-2018	17-01-2018

7. Demo	18-01-2018	18-01-2018